## Apr 23 - Mar 24
Forward Plan - Press Releases (Apr 23 - Mar 24)
Keighley
Project Name | Project Sponsor | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01
A-DIF | CBMDC
>Providence Park | MEFE | 2023-04-01: Press Release / GFA Signed; 2023-05-01: Project Start; 2023-07-01: Press release required; 2023-09-01: Press release required; 2023-11-01: Press release required
>Beechcliffe |  | 2023-09-01: GFA to be signed
>Victoria Hotel |  | 2023-09-01: GFA to be signed
B-Town Centre Infrastructure | CBMDC | 2023-06-01: Press Release
>Low Street Phase 2 |  | 2023-06-01: Project Start; 2023-10-01: Project Completion
>Connectivity Study
>Public Realm Improvements |  | 2024-01-01: Project Start
>Infrastructure - Active Travel |  | 2023-08-01: Project Start; 2023-12-01: Press release required; 2024-01-01: Press release required; 2024-02-01: Press release required; 2024-03-01: Project Completion
>Real Time Bus info |  | 2023-07-01: Press release required
C-Keighley Skills Hub | Keighley College | 2023-06-01: Decision due?; 2023-07-01: GFA to be signed; 2023-12-01: Project Start
D-Manufacturing Hub | Keighley College | 2023-06-01: GFA to be signed; 2023-07-01: Press release required
E-Capital Assistance to Business Growth | CBMDC |  | Press Release | Press release required | Press Release | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required
F - Community Grants - Keighley
>CG1 - River Worth Friends | River Worth Friends | 2023-07-01: GFA to be signed
>CG2 - Scott Street | Keighley Healthy Living | 2023-05-01: GFA Signed; 2023-06-01: Press release required; 2023-07-01: Project Start
>CG3 - Haworth Toilets | Haworth Parish Council | 2023-04-01: GFA Signed; 2023-06-01: Due to Open - Press Release
>CG4 - Keighley Cougars | Keighley Cougars | 2023-05-01: Press Release; 2023-09-01: GFA to be signed
>CG5 - Haworth Village Hall | Haworth Village Hall | 2023-04-01: Press Release; 2023-09-01: GFA to be signed
>CG6 - Sangat Centre | Sangat Centre | 2023-04-01: GFA Signed; 2023-05-01: Project Start; 2023-06-01: Project Underway; 2023-07-01: Project Underway
>CG7 - Woodville Activity Centre | Woodville Activity Centre | 2023-07-01: GFA to be signed; 2023-09-01: Project Start
>CG8 - Old School Room | Bronte Spirit | 2023-04-01: GFA Signed; 2023-05-01: Project Start; 2023-06-01: Project Underway; 2023-07-01: Press Release Project Completed
>CG9 - Central Hall | Central Hall | 2023-05-01: GFA Signed; 2023-07-01: Press Release; 2023-08-01: Project Start; 2023-09-01: Project Underway
>CG10 - Good Shepherd Centre | Good Shepherd Centre | 2023-07-01: GFA to be signed
>CG11 - Worth Valley Railway | KWVRR | 2023-06-01: GFA to be signed, Press release required; 2023-07-01: Project Start
G-Keighley Creative (ESA) | East Street Arts | 2023-08-01: GFA to be signed; 2023-09-01: Project Start
H-Women Employment Programme | KAWACC | 2023-07-01: GFA to be signed; 2023-09-01: Project Start
I-Keighley Art & Film Festival | Keighley Creative | Project Underway | Project Underway | Project Underway | Press release required | Project Underway | Project Underway | Project Underway | Project Underway | Project Underway | Project Underway | Project Underway | Project Underway
J-Community & Wellbeing Centre | NHS | 2023-05-01: Press Release; 2023-06-01: Decision made; 2023-09-01: GFA to be signed; 2023-12-01: Project Start
Shipley
A-DIF | CBMDC | 2023-09-01: GFA to be signed; 2024-01-01: Project Start
B-Town Centre Infrastructure | CBMDC
>Market Square |  | 2023-08-01: Project Start; 2024-01-01: Press release required
>Shipley Toilets |  | 2023-08-01: Project Start
>Canal Road
>Infrastructure - Active Travel |  | 2023-07-01: Press release required; 2023-08-01: Press release required; 2023-09-01: Press release required; 2023-10-01: Press release required
>Real Time Bus info
C-Community, Art & Tech Hub | Shipley College | 2023-04-01: Dec 22 Guardian Article; 2023-06-01: Decision due?; 2023-07-01: Planning Permission?; 2023-08-01: GFA to be signed
D-Capital Assistance for Business Growth | CBMDC |  | Press Release | Press release required | Press Release | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required | Press release required
E-Shipley Enterprise Library | CBMDC | 2023-04-01: Press Release; 2023-05-01: Press release required; 2023-06-01: Project Start; 2023-07-01: Press release required; 2023-08-01: Project Completion
F-Health & Wellbeing Campus | The Cellar Trust | 2023-05-01: Press Release; 2023-06-01: GFA to be signed
G-Wrose Quarry | Conservation Volunteers | 2023-05-01: Project Underway; 2023-06-01: Project Underway; 2023-07-01: Press Release; 2023-08-01: Project Underway; 2023-09-01: Project Underway; 2023-10-01: Project Underway
H-Shipley Sustainable Community Hub | OSBC | 2023-05-01: Planning permission approved; 2023-06-01: GFA to be signed; 2023-07-01: Project Start
Note on G13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Ingrow Lane, Bracken Bank (footway improvements on a route to school) is projected to start on site on 31st July and complete on the 18th August, subject to contractor to confirmation. Projected cost - £8k Reply: Bradford Road, Keighley (improvements to footway links to railway station) has been awarded to a contractor who has yet to confirm their acceptance. Projected cost - £6k
Note on K13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Swine Lane (carriageway widening/improvement) is projected to take place in late 2023 or early 2024. The scheme needs to be designed in association with ‘traffic and road safety’ colleagues to ensure that we achieve the best outcomes. There will be an element of new carriageway construction and possible utility diversions. Projected cost - £40k
Note on L13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Thwaites Brow Road (repairs and replacement of stone sett surface) is projected to start on site in January 2024 and complete in March 2024. This timeframe arises from the need for a specialist contractor for the stone setts. There will be a need to source replacement setts, but the Highway Team are exploring options to salvage existing setts from the road edge/top/bottom should sourcing not achieve desired quantities. There’s approximately 310m2 of missing setts that need to be purchased and laid to full construction depth. There are potentially 100m2 of setts that have settled and need lifting/relaying along with new construction beneath. Some of these setts may disintegrate on excavation and others may be unsuitable gauge width. Projected cost - £150k
Note on N13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Long Lee and the rights of way from Hillsides will need further design development before delivery, and will not be delivered by the Highways Maintenance (North) Team.
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Delivery of the additional real time bus information installations is from the West Yorkshire Combined Authority, who manage the bus stops infrastructure. Three further sites than those listed below are expected to be delivered using Towns Fund resources.
Note on G37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The intention is to make a start on site during summer 2023 and carry out certain “enabling” works during late summer/autumn 2023, some examples being:  Site Investigation works required for the public realm area and for canopy foundation design  Possible installation of electric charge points in the car park  Site clearance of trees to be removed in November  Localised paving repairs to Well Croft area which can be done using the Bradford Council’s term contract process. Perhaps also construction of the raised planters.  Install real time travel information to the existing Metro totem (Market Square/Bank Street)  Enabling works for the Market Service store extension
Note on L37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Projected programme: By the end of August - development of detailed design for the Shipley Marketplace public realm scheme, which will include paving, landscape, drainage, etc. September – preparation of contract documents to include drawings, bill of quantities, specifications, etc. October – tender period November – evaluation of bidders returns and Contract Award Early 2024 – main contract works to start of paving for the front of the shops and on the market area. The duration of main contract works on site will be phased to minimise disruption for businesses.
Note on F40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Victoria Park (footway improvements on a route to school) is complete. Cost - £39,312.05
Note on G40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Wrose Brow Road (footway improvements on a route to school) is scheduled to start on 31st July and complete 1 st September, before schools re-open for the new term. Projected cost - £16k
Note on H40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: West Lane, Baildon (footway improvements on a route to school) is scheduled to be delivered in September. Work has been measured and an order will be placed with a contractor shortly. No firm start date is yet confirmed pending confirmation of the contractor’s programmes, but early September anticipated. Projected cost - £8k
Note on I40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: West Royd Avenue (reconstructed footway) is scheduled to be delivered in September. Works have been measured and an order will be placed with a contractor shortly. No firm start date is yet confirmed pending confirmation of the contractor’s programmes, but early September anticipated. Projected cost - £10k

## Apr 24 - Mar 25
Forward Plan - Press Releases (Apr 24 - Mar 25)
Keighley
Project Name | Project Sponsor | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01 | 2024-12-01 | 2025-01-01 | 2025-02-01 | 2025-03-01
A-DIF | CBMDC
>Providence Park | MEFE
>Beechcliffe
>Victoria Hotel
B-Town Centre Infrastructure | CBMDC
>Low Street Phase 2
>Connectivity Study
>Public Realm Improvements
>Infrastructure - Active Travel
>Real Time Bus info
C-Keighley Skills Hub | Keighley College
D-Manufacturing Hub | Keighley College
E-Capital Assistance to Business Growth | CBMDC
F - Community Grants - Keighley
>CG1 - River Worth Friends | River Worth Friends
>CG2 - Scott Street | KHL
>CG3 - Haworth Toilets | Haworth Parish Council
>CG4 - Keighley Cougars | Keighley Cougars
>CG5 - Haworth Village Hall | Haworth Village Hall
>CG6 - Sangat Centre | Sangat Centre
>CG7 - Woodville Activity Centre | Woodville AC
>CG8 - Old School Room | Bronte Spirit
>CG9 - Central Hall | Central Hall
>CG10 - Good Shepherd Centre | Good Shepher Centre
>CG11 - Worth Valley Railway | KWVRR
G-Keighley Creative (ESA) | East Street Arts
H-Women Employment Programme | KAWACC
I-Keighley Art & Film Festival | Keighley Creative
J-Community & Wellbeing Centre | NHS
Shipley
A-DIF | CBMDC
B-Town Centre Infrastructure | CBMDC
>Market Square
>Shipley Toilets
>Canal Road
>Infrastructure - Active Travel
>Real Time Bus info
C-Community, Art & Tech Hub | Shipley College
D-Capital Assistance for Business Growth | CBMDC
E-Shipley Enterprise Library | CBMDC
F-Health & Wellbeing Campus | The Cellar Trust
G-Wrose Quarry | Conservation Voluneers
H-Shipley Sustainable Community Hub | OSBC